## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | (Fill your Project Number here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
48
Personal Health Assistant
SuryaQuantum AI
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (24 January – 30 January)
Deciding the MVP and appropriate Tech Stack | Requirements and Design | Team | 2 | 4 | Done
First Meet with the Client | Requirements | Team | 1 | 0.75 | Done
Refining the MVP and Tech Stack after meet | Requirements and Design | Team | 0.5 | 1 | Done
Dividing the Work and Making Weekly Plan | Coordination | Team | 2 | 3 | Done
Week 2
Setup Database and Implement PDF Upload | Development | Tanush | 2 | 3 | Done
Context Object and System Prompt Design | Development | Tanush | 1 | 0.5 | Done
Implement Stub Retrieval Function | Development | Tanush | 1 | 0.5 | Done
Mock retrieval stub | Development | Avnish | 1
Implement and test OCR functionality | Development | Rishabh | 1 | 1.5 | Done
Week 3
Week 4
Week 5
Week 6